## Sheet1
Rhode Island Greenhouse Gas Stakeholder Process 2006 Workplan
Raab Associates, Ltd. | [5 empty] | Consulting Costs
2006-01-01 |  |  |  | GHG |  | (Doesn't include facilitation time or meeting attendance)
|  |  |  | Reduction |  | Low | High
Sector | Option |  | Activities | Potential | Timing | -1000 | -1000
RGGI
Transportation | Companion to CA Clean |  | Could be "feebates", education, | Med/High | 2006 | 3 | 8
| Car GHG Rule |  | hybrid/efficient car incentive, other
Transportation | VMT Strategies |  | Advertise RIPTA |  |  | 1 | 10
Parking/Mass Transit cash out
|  |  | Develop PAYD Insurance Option | Medium | 2006
|  |  | Support Transit Oriented Devel. | Medium | 2006 and beyond
|  |  | Calculate Rebound Effect | NA
Transportation |  |  | Idling Reduction Strategies
Transportation | CAFÉ Standards |  | Support national increases in | Medium | 2006 and beyond | 1 | 3
CAFÉ standards for cars and SUVs/
Light Trucks
Buildings/ | Oil/Gas DSM SBC Fund |  | Develop legislation on oil SBC. | High | 2006 Leg. Session | 2 | 5
Facilities |  |  | Develop legislation or PUC regs.
on gas SBC
Buildings/ | School Construction |  | Develop LEED or comparable | Medium | 2006 | 2 | 5
Facilities | Execultive Order |  | Standard for School Construciton
Education | Education campaign |  | Review and fine tune material. | Medium | Start 2006, on-going. | 13.5 | 13.5
Help fundraise to promote.
Consider setting personal goal
20% reduction by 2020.
Consider doing polls before and
after or Deliberative Polling.
Modeling |  | Update modeling of baseline, and |  | NA |  | 25 | 25
GHG reductions from planned and
implemented programs.
Tracking System |  | Developing spreadsheet based |  | NA |  | 8 | 14
for tracking GHG by program
[6 empty] | 55.5 | 83.5
Sub-Total for Consulting (doesn't include facilitation or meeting costs)
Other Potential Projects if Funding Available
Buildings/ | Energy Building Codes |  | Advocate/Support improving | Medium | 2006 and successive cycles | 1 | 3
Facilities |  |  | commercial/res energy codes
Buildings/ | Compact Living/Appliances |  | Education on selecting right-sized | Medium | On-going | 2 | 5
Facilities |  |  | appliances, homes, etc.
Possilbly including incentives
Solid Waste | Commercial Contracting |  | Run workshop to explain concept | Low | 2006 | ? | ?
| for Recyling |  | and match providers and users.
Forestry | Multiple forest and urban |  | Pass along recs. To DEM and | Medium | On-going | ? | ?
| Report recommendations |  | Providence forester.
Push to implement measures
All | Cities and Town |  | Transfer executive orders on bldgs | Low | 2006 and beyond | ? | ?
| Executive Orders |  | and transportation for them to adopt
Buildings/ | Envir. Preferable Purchasing |  | Governor Signs Executive Order | Low | 2006 | 1 | 5
Buildings | Energy Star tax holiday
Buildings | Wx low income homes
State land use and solid waste plans would have GHG benefit, but need to be analyzed.